## Schedule Group2
No. | Tasks |  | Assignment | Progress | Status | March | [6 empty] | April
[6 empty] | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Export Dataset from Kaggle to JSON file |  | Yun | bar: March 25 to March 29; April 1 to April 2
| 1.1 | pre-processing the dataset | Yun
2 | Project Report Template |  | All | bar: March 25 to March 29; April 1 to April 2
3 | Data Model Design in Cassandra |  | All | 100% | Done | bar: March 25
4 | Environment Setup |  | Rajiv & Sajan | bar: March 25 to March 29; April 1 to April 2
| 4.1 | Install Spark in Docker | Rajiv & Sajan | bar: March 25 to March 29; April 1 to April 2
| 4.2 | Access Cassandara in Spark | Rajiv & Sajan | bar: March 25 to March 29; April 1 to April 2
| 4.3 | Build clusters for development | Rajiv & Sajan | bar: March 25 to March 29; April 1 to April 2
| 4.4 | Set up enviroment on all memebers | All | bar: April 2
5 | Prepare DDL for Cassandra |  | Sunpreet | bar: March 25 to March 29; April 1 to April 2
6 | Dump data to Cassandra DB |  | All | bar: March 25 to March 29; April 1 to April 2
| 6.1 | Import tools--Research | Yun | bar: March 25 to March 29; April 1 to April 2
| 6.2 | Import data & Check | All | bar: April 2 to April 4
7 | Design Queries for Cassandra |  | All | bar: April 2 to April 4
| 7.1 | Create views for Casssandra | Rajiv | bar: April 2 to April 4
| 7.2 | 2 DML for Cassandra(Insert & Delete) | Sajan | bar: April 2 to April 4
| 7.3 | 2 DML for Cassandra(2 Update) | Rajiv | bar: April 2 to April 4
| 7.4 | 2 DML for Cassandra(2 Queiries) | Sunpreet | bar: April 2 to April 4
| 7.5 | 2 DML for Cassandra(2 Queiries) | Yun | bar: April 2 to April 4
8 | API Choose & design |  | All | bar: April 2 to April 5
| 8.1 | Choose API(java?python?...) | Yun | bar: April 2 to April 4
| 8.2 | Design | All | bar: April 2
| 8.3 | Implementation | All | bar: April 3 to April 5
9 | Visualization |  | All
| 9.1 | Weka for visualiztion | Sunpreet | bar: April 8 to April 10
| 9.2 | Qlik for visualiztion | Sajan | bar: April 8 to April 10
| 9.3 | PowerBI for visualiztion | Rajiv | bar: April 8 to April 10
| 9.4 | Tableau for visualiztion | Yun | bar: April 8 to April 10
10 | Presentation & Report |  | All | bar: April 10 to April 12; April 15 to April 16